## unicity_q4_project_layout
Unicity's Q4 Project Layout
Quarter | Team | Task/Activity | Assigned To | Start Date | End Date | Expected Outcome | Status | Comments
Q4 2024 | Marketing | Social Media Campaign | Francis and Juliet | 2024-10-10 | 2024-11-01 | Reach 1K total social media followers by Dec 31st | In progress | Make new post on all social media platforms due by 22/10
Q4 2024 | Development | Website Responsiveness | Mobi | 2024-10-02 | 2024-10-12 | 1. Make official website fully responsive for easy user navigation 2. Remove all bugs and make all web pages fully functional. | In progress | Ensure mobile responsiveness
Q4 2024 | Operations | Event/Logistics Planning | Ekeoma | 2024-10-15 | 2024-11-10 | Pitch possible event location, catering, and ensure smooth operation | Not started | Begin event layout discussions
Q4 2024 | Sales | Partner Outreach | Babz | 2024-10-09 | 2024-10-31 | Secure 1 key partnerships to boost registrations on Unicity app | Not started | Outreach campaign starting
Q4 2024 | Design | Slides for Hackfest Showcase | Myles | 2024-09-25 | 2024-10-21 | Create more awareness for Unicity. Have more vendors and users sign up on the app. Market Unicity as the number 1 stop for all examination resources, goods, and services | In progress